## Slide 1
EXECUTIVE PROJECT HEALTH REVIEW
Portfolio Health, Trends & Risk Outlook
Monthly Synthesis — July 2026
Prepared by the Project Health Reporting Agent | Professional Services

## Slide 2
SLIDE 2
Executive Summary
2
Projects Reviewed
1 / 1
Red / Amber
68
Avg. Health Score
2/2
Status Overrides vs. Self-Report
The portfolio's average composite health score is 68/100. 2 of 2 projects carry an overall status that differs from what their own status sheet self-reports once schedule slippage, critical-path risk, and stakeholder comments are weighed together rather than read in isolation. Outokumpu- S2P Project is the portfolio's most urgent item, rated Red at a 58.7/100 composite score.
KEY TAKEAWAY FOR THE CLIENT
Self-reported schedule health is no longer a reliable single indicator across this portfolio — composite, multi-signal scoring is now the basis for governance decisions and client updates.
Professional Services | Confidential
2

## Slide 3
SLIDE 3
Portfolio Health at a Glance
RAG DISTRIBUTION
Chart: 
| Red | Amber | Green
RAG | 1 | 1 | 0
COMPOSITE HEALTH SCORE BY PROJECT
Chart: 
| Project_Plan_B | Outokumpu- S2P Project
Score | 76.5 | 58.7
Professional Services | Confidential
3

## Slide 4
SLIDE 4
Cross-Portfolio Trend Analysis
1
Self-reported status is systematically unreliable
2 of 2 projects show a computed RAG that diverges from their own Schedule Health field — in both directions (one overly optimistic, one overly pessimistic). This is a portfolio-wide pattern, not an isolated data-entry issue, and points to inconsistent local definitions of "Green" across PMs.
2
Critical-path risk is concentrated, not evenly spread
14 critical-path tasks across the portfolio are either Red or trending behind schedule. Where slippage exists, it clusters on the critical path rather than being spread evenly across the plan — the projects most at risk are at risk because of a small number of high-leverage tasks.
3
Slippage severity is rising with project maturity
Average delay where slippage exists is 10.8 days across the portfolio, with 53 open tasks already past their planned end date. Later-stage projects (higher % complete) show materially larger average delays than earlier-stage ones — schedule risk compounds rather than resolves as projects mature.
Professional Services | Confidential
4

## Slide 5
SLIDE 5
Emerging & Common Risks
HIGH
Critical-path slippage
Multiple projects carry delayed or Red critical-path tasks that directly threaten committed end dates.
MEDIUM
Pending approvals as silent blockers
Stakeholder comments repeatedly reference approvals and dependencies awaiting sign-off — a leading indicator that precedes visible schedule slippage.
MEDIUM
Inconsistent self-reported RAG
Local Schedule Health values are not comparable across projects, undermining portfolio-level roll-ups unless re-scored centrally.
HIGH
Completion-vs-timeline gap widening
At least one project shows completion trailing elapsed timeline by a double-digit percentage, with no compensating acceleration visible.
Professional Services | Confidential
5

## Slide 6
SLIDE 6
Recommendations
01
Standardize RAG scoring centrally
Adopt the composite scoring model portfolio-wide so status is comparable across PMs and projects, replacing locally-defined Schedule Health fields as the reporting source of truth.
02
Institute a critical-path escalation trigger
Any critical-path task slipping more than 5 business days should auto-generate a follow-up action, rather than waiting for the next weekly cycle.
03
Close the approval-latency gap
Track pending-approval comments as a distinct leading indicator and assign an SLA (e.g. 3 business days) before they convert into schedule slippage.
04
Weekly steering review for Red/Amber projects
Formalize a standing weekly checkpoint for any project below an 80 composite score until it returns to Green.
Professional Services | Confidential
6

## Slide 7
SLIDE 7
Projects Requiring Attention — Detail
Project | PM | Status | Score | Open Overdue Tasks | Critical Risk | Self-Report vs. Computed
Outokumpu- S2P Project | Aftab Hashambhai | Red | 58.7 | 28 | 12/15 | Green → Red
Project_Plan_B | Rajat Bothra | Amber | 76.5 | 25 | 2/50 | Red → Amber
METHODOLOGY NOTE
RAG status is calculated from a weighted composite of schedule slippage (30%), completion vs. elapsed timeline (20%), critical-path task health (20%), stakeholder blocker signals (15%), and milestone health (15%), with override rules that cap the rating when critical-path or blocker risk is severe. Full methodology available on request.
Data as of the most recent weekly extract for each project. Portfolio of 2 project(s) reviewed this cycle.
Professional Services | Confidential
7